## Sheet1
no. | Task | App | Type | Dev Status | Testing Status | FIX in Release Version | FIX in Release Build | Notes
1 | Add timeout duration in seconds on remote config | Mobile | Feature | Done | Done | 5.0.1 | 1000033714
2 | Space in search box not working | Mobile | Bug | Done | Done | 5.0.1 | 1000033714
3 | Shimmer overflow on brand screen | Mobile | Bug | Done | Done | 5.0.1 | 1000033714
4 | onboarding screen overflow | Mobile | Bug | Done | Done | 5.0.1 | 1000033714
5 | deal info bottom sheet overflow | Mobile | Bug | Done | Done | 5.0.1 | 1000033714
6 | Bottom navbar overflow | Mobile | Bug | Done | Done | 5.0.1 | 1000033714
7 | Change password is not working | Mobile | Bug | Done | Done | 5.0.0 | 1000033712 | Resolved via backend, no app update needed
8 | Show search "keyword" on search screen | Mobile | Feature | Done | Done | 5.0.1 | 1000033714
9 | Remove the search result limit list from the search screen | Mobile | Feature | Done | Done | 5.0.1 | 1000033714
10 | Homepage collectiion ordering | Mobile | Feature | Done | Done | 5.0.0 | 1000033712 | Resolved via backend, no app update needed
11 | Payment not working on sadapay and some other banks | Mobile | Bug | In-progress | Backlog | 5.0.1 | 1000033714
12 | Membership page can be access in logout state | Mobile | Bug | Done | Done | 5.0.1 | 1000033714
13 | Image uploading is not working on admin portal | Admin Portal | Bug | Backlog | Backlog | 5.0.1 | 1000033714
14 | Search auto complete not working properly when type while loading | Mobile | Bug | In-progress | Done | 5.0.1 | 1000033714
15 | Social Gmail is not working (Android 8). | Mobile | Bug | In-progress | Backlog | 5.0.1 | 1000033714
16 | When pressing the space bar in the search bar, results are shown. | Mobile | Bug | In-progress | Backlog | 5.0.1 | 1000033714
17 | Shimmer effect on the home screen. | Mobile | Bug | In-progress | Done | 5.0.1 | 1000033714
18 | "Your request timed out" message appears randomly. | Mobile | Bug | In-progress | Done | 5.0.1 | 1000033714
19 | "Confirm Location" text overflows in full font. | Mobile | Bug | In-progress | Backlog | 5.0.1 | 1000033714
20 | Shimmer effect appears when tapping on the membership card. | Mobile | Bug | In-progress | Backlog | 5.0.1 | 1000033714
21 | Display voucher code in success popup & in redemptions history for record keeping | Mobile | Feature | Backlog | Backlog | 5.0.1 | 1000033714
22 | If a merchant allows you to use multiple vouchers in a single billing, it should be integrated in a way that is seamlessly known to the user from the app, such that they don't have to ask someone | Mobile | Feature | Backlog | Backlog | 5.0.1 | 1000033714
23 | The system allows an invalid email address with double ".com" to be updated successfully, and the user can log in with this incorrect email format. | Mobile | Feature | Backlog | Backlog
24 | Set a New Password screen alignment is out in full font size | Mobile | Bug | Backlog | Backlog
25 | Email update with a double .com succeeds, but social login fails with an "Email already exists" error. | Mobile | Bug | Backlog | Backlog
26 | The update button is moving on the Edit Profile screen and when you tap the button, it changes to "Updating..." and then back to "Update." | Mobile | Bug | Backlog | Backlog

## BOGO VISA INTEGRATION
TC-ID | TESTSCENARIO | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT
TC-1 | Verify that the user can navigate to the Visa membership screen | 1. Log in to the app. 2. Navigate to the membership screen. 3. Click on the membership button. | The user should be redirected to the Visa subscription screen. | Working as expected
TC-2 | Verify that the user can enter valid Visa card details | 1. On the Visa subscription screen, enter a valid Visa card number. 2. Enter expiry date and CVC. 3. Enter the cardholder name. | The system should accept the details and allow the user to proceed. | Working as expected
TC-3 | Verify error message when entering an invalid Visa card number | 1. Enter an incorrect or fake Visa card number. 2. Enter other card details and click "Verify". | The system should display an error message indicating invalid card details. | We are sorry your bank is currently not a part of the Bogo Liv VISA Membership Program, error appear at the bottom
TC-4 | Verify membership assignment based on card type | 1. Enter a Visa Classic card and verify membership. 2. Enter a Visa Gold card and verify membership. 3. Enter a Visa Platinum card and verify membership. | The system should assign Classic, Gold, or Platinum membership based on the entered card type. | Only VISA Gold credentials were provided and they are working OK.
TC-5 | Verify that Rs. 5 is deducted for card verification | 1. Enter a valid Visa card. 2. Tap on "Verify". | The system should deduct Rs. 5 from the user’s card for verification. | Pending, Cannot be verified
TC-6 | Verify that the deducted Rs. 5 is refunded after verification | 1. Complete the card verification process. 2. Check the user’s transaction history. | The Rs. 5 should be refunded to the user. | Pending, Cannot be verified
TC-7 | Verify that Visa-only merchants are visible to Visa users | 1. Log in with a non-Visa user account. 2. Navigate to merchants. 3. Log in with a Visa user account and navigate to merchants. | Only Visa users should be able to see Visa-only merchants.
TC-8 | Verify that Visa-only deals are visible to Visa users | 1. Log in with a non-Visa user account and check deals. 2. Log in with a Visa user account and check deals. | Visa-only deals should be visible only to Visa users.
TC-9 | Verify the redemption process for Visa deals | 1. Scan a Visa deal at checkout. 2. Verify the masked card and user initials. 3. Proceed with payment using the Visa card. | The cashier should validate the membership, and the deal should be applied successfully.
TC-10 | Verify that redeemed deals are locked for the day | 1. Redeem a Visa deal. 2. Try to redeem the same deal again within the same day. | The system should prevent the user from redeeming the same deal twice in a day.

## Membership Upgrade
BOGO liv
MEMBERSHIP UPGRADE TESTING
POSITIVE TESTCASES
TC-ID | TESTSCENARIO | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | RESULT
TC-1 | Verify tapping "Upgrade" redirects correctly | Tap on the "Upgrade" button from offer screen | User is redirected to invitation code screen | Working as Expected | PASS
TC-2 | Verify valid invitation code allows next step | Enter valid invitation code → Tap Apply | Code accepted → redirected to payment screen | Working as Expected | PASS
TC-3 | Verify membership details display correctly | Tap "Upgrade" → Apply code → Review membership details | Correct membership name (Platinum/Junoon) and price shown | Working as Expected | PASS
TC-4 | Verify valid card credentials complete payment | Enter card info → Tap Confirm | Payment successful and upgrade done | Working as Expected | PASS
TC-5 | Verify confirmation message appears post-upgrade | Complete successful upgrade | Success message/popup appears | Working as Expected | PASS
TC-6 | Verify upgraded status reflects immediately | After upgrade, go to profile/home screen | Updated membership tier shown instantly | Working as Expected | PASS
TC-7 | Verify locked offers are now unlocked | Check locked offers before and after upgrade | Offers become accessible post-upgrade | NOT WORKING | FAIL
TC-8 | Verify access to exclusive offers post-upgrade | Upgrade membership → Navigate to exclusive offers | Exclusive content now accessible | NOT WORKING | FAIL
NEGATIVE TESTCASES
TC-ID | TESTSCENARIO | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | RESULT
TC-1 | Invalid invitation code behavior | Enter invalid/expired code (e.g., 00000000) → Tap Apply | Error message shown, no redirection | Invite NOT found error appears | PASS
TC-2 | Invalid card details handling | Enter wrong card number or CVV → Tap Confirm | Payment fails with proper error message | Something went wrong appeared | PASS
TC-3 | No internet during upgrade | Turn off internet → Try upgrade process | Appropriate error shown or retry option | Something went wrong , Try again appeared | PASS
TC-4 | Back tap during upgrade | Start upgrade → Tap back in any step | Navigation handled gracefully, no crash | Working as Expected | PASS
TC-5 | Prevent double upgrade | Try to upgrade again after already being upgraded | Message shown like "You are already a member" | No error appear. User is able to do double Upgrade | FAIL
TC-6 | Check secure handling of payment data | Observe UI and behavior during/after card input | No sensitive data shown or stored | Working as Expected | PASS
EDGE TESTCASES
TC-ID | TESTSCENARIO | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT
TC-1 | App killed mid-payment | Start upgrade → Payment screen → Kill app → Reopen | Membership upgrade either completed or reattempt prompt shown | TO BE CONTINUE
TC-2 | Invitation code field behavior | Try submitting with and without invitation code | System enforces expected behavior (required or optional)
TC-3 | Check upgrade notifications | Complete upgrade → Check for SMS/Email | User receives confirmation message
TC-4 | Same code used by multiple users | Share same code → Apply on two accounts | Proper limit handling and message if reuse not allowed
TC-5 | Simultaneous upgrade on two devices | 1. Login same account on two devices 2. Start upgrade on both at same time | Should handle concurrency; one upgrade should be processed only

## Sheet5
BOGO liv
FEATURES FOR TESTING:
1- | Startup Optimization
2- | User Addresses
3- | Remote Config – API JSON Refactored
4- | Authentication Shifted to V2
5- | Visa Membership
6- | Offer Screen Refactored
7- | Membership Upgradation
8- | Store Card UI
9- | Membership Theming Refactor
10- | Invalid Payment Popup (in App Settings for Upgrade Membership)
11- | Overall API Call Testing
STARTUP OPTIMIZATION |  |  |  |  | startup optamisation
SNO. | Test Case | Steps | Expected Result | Actual Result | user addresses
TC-1 | Verify app launch time | Close and relaunch the app multiple times | App launches within 2–3 seconds | Working OK | remote config > api json refactored
TC-2 | Verify no splash screen freeze | Open app after cold start | No freezing or blank screens | Working OK | auth shifted t0 v2
USER ADDRESSES |  |  |  |  | visa membership
SNO. | Test Case | Steps | Expected Result | Actual Result | offer screen refactored
TC-3 | Add address | Tap on Location appearing at top > add new | Address is saved and appears in list | Not working ok. Keypad is not appearing once all the content is removed (inconsistent behaviour) | membership upgradtion
TC-4 | Edit address | Tap on existing > edit > save | Changes reflect instantly | Working ok | store card UI
TC-5 | Delete address | Tap delete > confirm | Address is removed from list | Working ok | membership theming refactoring
TC-6 | Logout/Login check | Add address > logout > login | Address remains in account correctly | Working ok | add invalidPaymentPopup to appSettings (for upgrade membership)
AUTH SHIFTED TO V2 |  |  |  |  | remote config > api json refactored
SNO. | Test Case | Steps | Expected Result | Actual Result | ise apko overall app ki api call test karni hongi.
TC-7 | Login with valid credentials | Email + password | User is logged in successfully | Working ok
TC-8 | Signup with new email | Fill valid details | Account is created | Working ok
TC-9 | Forgot password | Enter registered email | OTP/code is sent | Working ok
TC-10 | Invalid credentials | Wrong password or email | Error message shown | Working ok
VISA MEMBERSHIP
SNO. | Test Case | Steps | Expected Result | Actual Result
TC-11 | Verify navigation to Visa membership screen | Login > Go to Membership > tap on get VISA membership | User is navigated to Visa screen | Working Ok
TC-12 | Verify user can enter Visa card details | On Visa screen, enter valid Visa card number (starting digits) & tap Confirm | Card details accepted without errors | Working Ok
TC-13 | Verify membership type based on card | Enter Visa Classic/Gold/Platinum card | Correct membership type is shown (Classic/Gold/Platinum) | membership is shown upon refreshing
TC-14 | Verify 5 Rs deduction & refund logic | Complete card verification process | Rs5 is deducted and auto-refunded | Cannot be verify in staging env
TC-15 | Verify successful upgrade | Finish process and return to home | Membership status shows upgraded to respective tier | membership is shown upon refreshing
TC-16 | Verify exclusive Visa deals visibility | Go to Explore/Deals | Exclusive Visa deals appear only for Visa members | Working Ok
TC-17 | Verify error on invalid card | Enter wrong or non-Visa card | App shows "Invalid Card" error | working Ok
TC-18 | Verify retry logic if card fails first time | Submit failed card → Retry | Retry works, and proper error handling shown
TC-21 | Verify deal redemption using Visa | Tap a Visa deal → Scan at store | Deal redeemed after successful Visa payment | working Ok
VISA MEMBERSHIP
SNO. | Test Case | Steps | Expected Result | Actual Result
TC-22 | Open offers | Navigate to offer screen | Deals load correctly | working ok
TC-23 | Tap a deal | Select any offer | Redirects to deal details page | working ok
TC-24 | Membership-based visibility | Use normal vs Visa account | Exclusive offers show only for Visa | working ok
OFFER SCREEN REFACTORED
SNO. | Test Case | Steps | Expected Result | Actual Result
TC-25 | Verify Offer screen loads successfully | Open app → Tap on “Offers” from home or bottom tab | Offer screen loads without crash or delay | Working ok
TC-26 | Verify all available offers are listed properly | Open Offer screen | Offers are displayed clearly with images, titles & descriptions | Working ok
TC-27 | Verify offer tap leads to deal details | Tap on any offer | User is navigated to detailed offer screen | Working ok
TC-28 | Verify valid membership restrictions on offers | Tap on an offer limited to Gold or Platinum | Non-eligible users see restriction popup/message | Working ok
TC-29 | Verify exclusive offers are shown correctly (e.g. Visa, Gold etc.) | Open Offer screen with a Visa or Platinum account | Exclusive offers appear only for eligible users | Working ok
TC-30 | Verify search/filter on offers (if available) | Use search bar or filters | Only matching offers are displayed | Not working wrt filters
TC-31 | Verify layout and UI elements after refactor | Check spacing, fonts, and buttons | UI should match new design with no overlap or glitches
TC-32 | Verify offer redemption works from offer screen | Tap → View deal → Redeem | Deal can be redeemed successfully | Working ok
TC-33 | Verify back button and navigation flow | Tap on offer → Go back | User returns to Offer screen smoothly | Working ok
MEMBERSHIP UPGRADATION
SNO. | Test Case | Steps | Expected Result | Actual Result
TC-34 | Verify tapping "Upgrade" redirects correctly | Tap on the "Upgrade" button from offer screen | User is redirected to invitation code screen | Working as Expected
TC-35 | Verify valid invitation code allows next step | Enter valid invitation code → Tap Apply | Code accepted → redirected to payment screen | Working as Expected
TC-36 | Verify membership details display correctly | Tap "Upgrade" → Apply code → Review membership details | Correct membership name (Platinum/Junoon) and price shown | Working as Expected
TC-37 | Verify valid card credentials complete payment | Enter card info → Tap Confirm | Payment successful and upgrade done | Working as Expected
TC-38 | Verify confirmation message appears post-upgrade | Complete successful upgrade | Success message/popup appears | Working as Expected
TC-39 | Verify upgraded status reflects immediately | After upgrade, go to profile/home screen | Updated membership tier shown instantly | Working as Expected
TC-40 | Verify locked offers are now unlocked | Check locked offers before and after upgrade | Offers become accessible post-upgrade | NOT WORKING
TC-41 | Verify access to exclusive offers post-upgrade | Upgrade membership → Navigate to exclusive offers | Exclusive content now accessible | NOT WORKING
Invalid Payment Popup (in App Settings for Upgrade Membership)
SNO. | Test Case | Steps | Expected Result | Actual Result
TC-42 | Use invalid card | Upgrade flow > wrong card | "Invalid payment" popup shown | Something went wrong appeared
TC-43 | No internet | Upgrade flow > disconnect net | Appropriate error popup shown | Something went wrong appeared
Membership Theming Refactor
SNO. | Test Case | Steps | Expected Result | Actual Result