## Testcases
INNER CREW
TC-ID | TEST SCENARIO | PRE-CONDITONS | TEST STEPS | EXPECTED RESULTS | ACTUAL RESULT | STATUS | BUILD | COMMENTS
LOGIN SCREEN
TC-1 | Verify "Enter Email" field | App is launched | 1. Enter a valid email. | The field accepts the input without showing an error. | Incorrect Email or Password toast is shown | PASS | 1.0.0.4
TC-2 | Validate invalid email | App is launched | 1. Enter an invalid email format (e.g., "abc@com"). | An error message is displayed. | Please provide a valid email validation appears | PASS | 1.0.0.4
TC-3 | Verify password masking | App is launched | 1. Enter a password in the "Enter Password" field. | The password is masked (dots or asterisks are shown). | Working as expected. | PASS | 1.0.0.4
TC-4 | Toggle password visibility | App is launched | 1. Enter a password. 2. Click the eye icon. | Password visibility toggles between masked and plain text. | Working as expected. | PASS | 1.0.0.4
TC-5 | Forgot Password link | App is launched | 1. Click on the "Forgot Password?" link. | The user is navigated to the password recovery screen. | Working as expected. | PASS | 1.0.0.4
TC-6 | Verify Sign-in button with valid input | App is launched, valid credentials are available | 1. Enter valid email and password. 2. Click the "Sign in" button. | The user is successfully authenticated and navigated to the app. | Working as expected. | PASS | 1.0.0.4
TC-7 | Verify Sign-in button with invalid input | App is launched | 1. Enter invalid email or password. 2. Click the "Sign in" button. | An error message is displayed, and login is unsuccessful. | Working as expected. | PASS | 1.0.0.4
TC-8 | Register link navigation | App is launched | 1. Click on the "Register" link. | The user is navigated to the registration screen. | Working as expected. | PASS | 1.0.0.4
TC-9 | Google sign-in button | App is launched | 1. Click on the Google icon. | The user is redirected to the Google authentication page. | Working as expected. | PASS | 1.0.0.4
TC-10 | Facebook sign-in button | App is launched | 1. Click on the Facebook icon. | The user is redirected to the Facebook authentication page. | ERROR page is shown | FAIL | 1.0.0.4
TC-11 | UI layout and alignment | App is launched | 1. Inspect the layout and alignment of all elements on the screen visually. | All elements are properly aligned and displayed without overlapping. | Alignment is NOT ok | FAIL | 1.0.0.4 | Not as per Figma
FORGOT PASSWORD SCREEN
TC-12 | Verify "Enter Email" field functionality | App is launched, Forgot Password screen is opened | 1. Enter a valid email address. | The email is accepted without error. | Working as expected. | PASS | 1.0.0.4
TC-13 | Validate invalid email format | App is launched, Forgot Password screen is opened | 1. Enter an invalid email format (e.g., "abc@com"). | An error message is displayed indicating the email format is invalid. | Please provide a valid email validation appears | PASS | 1.0.0.4
TC-14 | Verify Reset Password button with valid email | App is launched, Forgot Password screen is opened | 1. Enter a valid email. 2. Click on "Reset password". | A success message is displayed, and the password reset process is initiated. | Success Msg is shown but for now OTP/CODE is sent on specific emails only. | WIP | 1.0.0.4
TC-15 | Verify Reset Password button with invalid email | App is launched, Forgot Password screen is opened | 1. Enter an invalid or non-registered email. 2. Click on "Reset password". | An error message is displayed indicating the email is not registered. | Enter Registered Email toast is shown, working as expected | PASS | 1.0.0.4
TC-16 | Verify navigation to Login screen | App is launched, Forgot Password screen is opened | 1. Click on "Back to Login". | The user is navigated back to the Login screen. | Working as expected. | PASS | 1.0.0.4
TC-17 | UI layout and alignment | App is launched, Forgot Password screen is opened | 1. Inspect the layout and alignment of all elements on the screen visually. | All elements are properly aligned and displayed without overlapping. | Alignment is NOT ok | FAIL | 1.0.0.4 | Not as per Figma
REGISTER SCREEN
TC-18 | Verify "Enter First Name" field functionality | App is launched, Register screen is opened | 1. Enter a valid first name. | The first name is accepted without error. | Working as expected. | PASS | 1.0.0.4
TC-19 | Verify "Enter Last Name" field functionality | App is launched, Register screen is opened | 1. Enter a valid last name. | The last name is accepted without error. | Working as expected. | PASS | 1.0.0.4
TC-20 | Validate empty "First Name" field | App is launched, Register screen is opened | 1. Leave the "First Name" field empty. 2. Click on "Next." | An error message is displayed indicating the field cannot be empty. | Please filled out this field validation appears | PASS | 1.0.0.4
TC-21 | Validate empty "Last Name" field | App is launched, Register screen is opened | 1. Leave the "Last Name" field empty. 2. Click on "Next." | An error message is displayed indicating the field cannot be empty. | Please filled out this field validation appears | PASS | 1.0.0.4
TC-22 | Verify navigation to Sign-In screen | App is launched, Register screen is opened | 1. Click on "SIGN IN" at the bottom of the screen. | The user is navigated to the Sign-In screen. | Working as expected. | PASS | 1.0.0.4
TC-23 | Verify "Next" button with valid data | App is launched, Register screen is opened | 1. Enter valid first and last names. 2. Click on "Next." | The user is navigated to the next registration step or screen. | The user is successfully navigated to Provide additional information screen | PASS | 1.0.0.4
TC-24 | Verify Valid information entry | User is on the Provide Additional Information screen after successfully entering their first and last name on the previous screen. | 1. Enter a valid email (e.g., test@example.com) in the Email field. 2. Enter a valid password (e.g., Password@123). 3. Re-enter the same password. 4. Check the I accept terms and conditions box. 5. Click Register. | The user is successfully registered and navigated to the next screen (e.g., Dashboard or confirmation screen). | Working as expected. | PASS | 1.0.0.4
TC-25 | Verify Missing email | User is on the Provide Additional Information screen. | 1. Leave the Email field empty. 2. Enter valid passwords in both password fields. 3. Check the I accept terms and conditions box. 4. Click Register. | An error message appears: "Email is required." | Enter a valid email validation appears | PASS | 1.0.0.4
TC-26 | Verify Invalid email format | User is on the Provide Additional Information screen. | 1. Enter an invalid email (e.g., test.com) in the Email field. 2. Enter valid passwords in both password fields. 3. Check the I accept terms and conditions box. 4. Click Register. | An error message appears: "Enter a valid email address." | Please provide a valid email validation appears | PASS | 1.0.0.4
TC-27 | Verify Missing password | User is on the Provide Additional Information screen. | 1. Leave the Password field empty. 2. Enter the same password in the Re-enter Password field. 3. Enter a valid email. 4. Check the I accept terms and conditions box. 5. Click Register. | An error message appears: "Password is required." | Enter a Password and Passwords must match validations appears | PASS | 1.0.0.4
TC-28 | Verify Password mismatch | User is on the Provide Additional Information screen. | 1. Enter a valid email. 2. Enter Password@123 in the Password field. 3. Enter Password@456 in the Re-enter Password field. 4. Check the I accept terms and conditions box. 5. Click Register. | An error message appears: "Passwords do not match." | Password must match validation appears | PASS | 1.0.0.4
TC-29 | Verify Weak password | User is on the Provide Additional Information screen. | 1. Enter a valid email. 2. Enter 12345 in the Password field. 3. Re-enter the same password. 4. Check the I accept terms and conditions box. 5. Click Register. | An error message appears: "Password must meet the strength requirements." (e.g., minimum 8 characters, uppercase, lowercase, number, special character). | Password should be atleast 6 characters validation appears in both fields | PASS | 1.0.0.4
TC-30 | Verify Unchecked terms and conditions checkbox | User is on the Provide Additional Information screen. | 1. Enter a valid email. 2. Enter a valid password and re-enter it. 3. Do not check the I accept terms and conditions box. 4. Click Register. | An error message appears: "You must accept the terms and conditions to proceed." | Please accept terms and condition to proceed toast appears | PASS | 1.0.0.4
TC-31 | Verify Email already in use | User is on the Provide Additional Information screen. | 1. Enter an already registered email (e.g., test@example.com). 2. Enter valid passwords. 3. Check the I accept terms and conditions box. 4. Click Register. | An error message appears: "Email is already registered. Please log in or use a different email." | User with this email already exists toast appears | PASS | 1.0.0.4
TC-32 | Verify Successful registration with all valid inputs | User is on the Provide Additional Information screen. | 1. Enter a valid email. 2. Enter a strong password. 3. Re-enter the same password. 4. Check the I accept terms and conditions box. 5. Click Register. | The user is registered successfully and navigated to the next screen. | Working as expected. | PASS | 1.0.0.4
TC-33 | Verify Maximum email length check | User is on the Provide Additional Information screen. | 1. Enter an email longer than 254 characters in the Email field. 2. Enter valid passwords. 3. Check the I accept terms and conditions box. 4. Click Register. | An error message appears: "Email address exceeds the maximum length allowed." | i exceeded the length and entered so many .com.com, the account was created successfully | FAIL | 1.0.0.4 | As per discussion with Ahmed, Email could be abc@rt.com.eu.io but character length will be set to 50 characters
TC-34 | Verify Password length check | User is on the Provide Additional Information screen. | 1. Enter a valid email. 2. Enter a password shorter than the required minimum length (e.g., 7 characters if the minimum is 8). 3. Re-enter the same password. 4. Check the I accept terms and conditions box. 5. Click Register. | An error message appears: "Password must be at least 8 | Password should be at least 6 characters validation appears | PASS | 1.0.0.4
TC-35 | UI layout and alignment | App is launched, Register screen is opened | 1. Inspect the layout and alignment of all elements on the screen visually. | All elements are properly aligned and displayed without overlapping. | Alignment is NOT ok | FAIL | 1.0.0.4 | Not as per Figma
TC-36 | Validate maximum character limit for fields | App is launched, Register screen is opened | 1. Enter more than 50 characters in the "First Name" and "Last Name" fields. | An error message is displayed or input is restricted after the limit. | It doesn't show any error and navigate to Provide Additional Information screen | FAIL | 1.0.0.4
TC-37 | Validate special characters in name fields | App is launched, Register screen is opened | 1. Enter special characters (e.g., "@#$%") in the name fields. | An error message is displayed indicating invalid input. | It doesn't show any error and navigate to Provide Additional Information screen | FAIL | 1.0.0.4
HOME SCREEN
TC-38 | Verify default state of the Home screen | User has no contacts added | 1. Open the app. 2. Navigate to the Home screen. | The screen displays: - App logo - Message: "Seems like you haven't added any contacts yet." - "Add people" button. | Working as expected. | PASS | 1.0.0.4
TC-39 | Verify "Add people" button functionality | User is on the Home screen | 1. Tap the "Add people" button. | User is navigated to the "Add Contact" screen. | Working as expected. | PASS | 1.0.0.4 | Black color floating button of Add your first contact is appearing on Add Contact screen
TC-40 | Verify Home screen with added contacts | User has contacts added to crews | 1. Add contacts to any crew. 2. Open the Home screen. | The Home screen displays upcoming reminders and activities for added contacts. | Working as expected. | PASS | 1.0.0.4
TC-41 | Verify app logo visibility | User is on the Home screen | 1. Open the Home screen. | The app logo ("INNER CREW") is displayed at the top of the screen. | Working as expected. | PASS | 1.0.0.4
TC-42 | Verify Home screen navigation | User is on a different screen | 1. Tap the "Home" icon from the bottom navigation bar. | User is navigated back to the Home screen. | Working as expected. | PASS | 1.0.0.4
TC-43 | Verify message for no contacts added | User has no contacts in any crew | 1. Open the Home screen. | The message "Seems like you haven't added any contacts yet" is displayed. | Working as expected. | PASS | 1.0.0.4
TC-44 | Verify the default state of the Home screen when contacts are added in crew | User has calls (pending and upcoming) | 1. Open the app. 2.Navigate to the Home screen. | The screen displays: - Pending Calls section - Upcoming Calls section - Filter and call details. | Working as expected. | PASS | 1.0.0.4
TC-45 | Verify the "Filter by" dropdown functionality | User is on the Home screen | 1. Tap the "Filter by" dropdown. 2. Select an option (e.g., All, Pending, Upcoming). | The list of calls updates based on the selected filter option. | Working as expected. | PASS | 1.0.0.4
TC-46 | Verify call details for pending calls | User has pending calls | 1. Tap on a pending call card. 2. View the details. | The call card displays: - Call name - Crew name - Due date/time - Contact details. | Working as expected. | PASS | 1.0.0.4
TC-47 | Verify call action buttons functionality | User is on the Home screen | 1. Locate a call card. 2. Tap the call icon. | The call is initiated. | Working as expected. | PASS | 1.0.0.4
TC-48 | Verify snooze functionality for calls | User is on the Home screen | 1. Tap the snooze icon for a call card. 2. Select a new time/date. | The call is rescheduled, and the new time/date is reflected on the card. | Working as expected. | PASS | 1.0.0.4
TC-49 | Verify marking a call as completed | User has a pending call | 1. Tap the checkmark icon on a pending call card. | The call is marked as completed, and the card moves out of the Pending Calls section. | Working as expected. | PASS | 1.0.0.4
TC-50 | Verify "View more details" functionality | User is on the Home screen | 1. Tap "View more details" on a call card. | Additional details for the call are displayed (e.g., call history, notes, etc.). | Working as expected. | PASS | 1.0.0.4
TC-51 | Verify the Upcoming Calls section | User has upcoming calls | 1. Open the Home screen. | Upcoming calls are displayed with details (e.g., call name, time, crew, status). | Working as expected. | PASS | 1.0.0.4
TC-52 | Verify pending call overdue label | User has overdue calls in Pending Calls | 1. Open the Home screen. | The overdue calls are marked with labels like "Due 6 days ago" or "Due 2 days ago." | Working as expected. | PASS | 1.0.0.4
TC-53 | Verify Upcoming Calls label | User has upcoming calls | 1. Open the Home screen. | The calls in the Upcoming Calls section are labeled with future statuses like "4 days later." | Working as expected. | PASS | 1.0.0.4
TC-54 | Verify no contact history message | User has a contact without call history | 1. View a call card for the contact without history. | "No contact history" message is displayed for the contact. | Working as expected. | PASS | 1.0.0.4
TC-55 | Verify notification bell functionality | User has a reminder | 1. Tap the bell icon at the top right corner. | User is navigated to the notification screen displaying relevant reminders. | Working as expected. | PASS | 1.0.0.4
TC-56 | Verify that the group color (e.g., "Family") displayed in the Contact Summary popup is dynamic and matches the group type. | User is on the Home screen | 1- Navigate to the Home screen. 2- Tap on a contact card (e.g., "Call A"). 3- Observe the Contact Summary section, particularly the group tag color. | The group color (e.g., "Family") displayed in the Contact Summary popup should be dynamic and matches the group type. | The group color (e.g., "Family") displayed in the Contact Summary popup is STATIC and doesnot matches the group type. | FAIL | 1.0.0.4
CONTACT SCREEN
TC-58 | Verify default state of Contacts screen | User is logged into the app | 1. Open the app. 2. Navigate to the Contacts screen. | The screen displays: - "Search contact" bar - Crews (e.g., Family, Work, Friends) - Empty contact state. | Working as expected. | PASS | 1.0.0.4
TC-59 | Verify "Search contact" functionality | User has multiple contacts added | 1. Enter a valid name in the "Search contact" bar. 2. Check search results. | Only contacts matching the entered name are displayed. | Search functionality is NOT working | FAIL | 1.0.0.4
TC-60 | Verify "New contact" button | User is on the Contacts screen | 1. Tap the "+ New contact" button. | User is navigated to the "Add Contact" screen. | Working as expected. | PASS | 1.0.0.4
TC-61 | Verify crew selection functionality | User is on the Contacts screen | 1. Tap on a specific crew (e.g., Family, Work). | Contacts related to the selected crew are displayed. | Working as expected. | PASS | 1.0.0.4
TC-62 | Verify "View Crew" button | User is on the Contacts screen | 1. Tap the "VIEW CREW" link. | User is navigated to the Crew details screen. | Working as expected. | PASS | 1.0.0.4
TC-63 | Verify adding a new contact to a crew | User is on the "Add Contact" page | 1. Tap "+ New contact". 2. Enter contact details. 3. Select a crew. 4. Save. | The new contact is displayed in the selected crew's list. | Working as expected. | PASS | 1.0.0.4
TC-64 | Contact Duplication Across Accounts and Grey Screen Display | User is on the "Add Contact" page | 1. Log in to Account A. 2. Save a new contact in Account A. 3. Log out of Account A. 4. Log in to Account B. 5. Check the contact list in Account B. 6. Tap on the duplicated contact in Account B. | Contacts should only be saved to the account where they were created. Tapping on any contact should display its details without issues. | The contact saved in Account A is duplicated in Account B. When tapping on the duplicated contact, a grey screen appears instead of contact details. | FAIL | 1.0.0.4 | When a contact is saved in one account, it gets copied to another account. Additionally, when tapping on the duplicated contact, a grey screen is displayed.
TC-65 | Verify "No contacts available" message | User has no contacts added | 1. Open the app. 2. Navigate to the Contacts screen. | The message "no contacts available" is displayed under the selected crew. | Working as expected. | PASS | 1.0.0.4
TC-66 | Verify empty search results message | User has no matching contacts | 1. Enter a name not present in the contact list. | A message indicating "no results" is displayed. | Its showing all the contacts of the specific crew on empty search | FAIL | 1.0.0.4
TC-67 | Verify floating "+" button | User is on the Contacts screen | 1. Tap the "+" floating button in the bottom-right corner. | User is navigated to the "Add Contact" screen. | Working as expected. | PASS | 1.0.0.4
TC-68 | Verify frequency display under crews | User has contacts with frequencies | 1. Open the Contacts screen. | Each crew displays the associated frequency (e.g., Weekly) correctly under its name. | Working as expected. | PASS | 1.0.0.4
ADD NEW CONTACT SCREEN
TC-69 | Verify UI elements are displayed correctly | User is on Add Contact screen | Open the "Add New Contact" screen. | All fields (First Name, Last Name, Phone Number, Email), buttons, and upload photo icon are displayed. | Working as expected. | PASS | 1.0.0.4
TC-70 | Verify "Upload Photo" icon functionality | User is on Add Contact screen | Tap on the "Upload Photo" icon. | The device's photo gallery or camera option opens. | Working as expected. | PASS | 1.0.0.4
TC-71 | Verify invalid characters in First Name field | User is on Add Contact screen | Enter special characters or numbers in the First Name field (e.g., "@John123"). | An error message is displayed, and the input is not accepted. | Contact added successfully | TBD | 1.0.0.4
TC-72 | Verify empty First Name/Last Name field behavior | User is on Add Contact screen | Leave the First Name and Last Name fields blank and attempt to create a contact. | An error message is displayed, and the contact is not created. | Validation only appears at First Name field | TBD | 1.0.0.4 | Contact is created successfully when user only enter the First Name and Leave Last Name, Contact # and Email field empty
TC-73 | Verify Phone Number field accepts valid input | User is on Add Contact screen | Enter a valid phone number (e.g., "+198123456789"). | The input is accepted without errors. | Working as expected. | PASS | 1.0.0.4
TC-74 | Verify invalid phone number input | User is on Add Contact screen | Enter an invalid phone number (e.g., too short or letters). | An error message is displayed, and the input is not accepted. | Contact added successfully, even after entering special characters, the contact is saved successfully | TBD | 1.0.0.4
TC-75 | Verify "+Add New" functionality for Phone Numbers | User is on Add Contact screen | Tap "+Add New" in the Phone Number section and add another number. | A new Phone Number field appears, allowing multiple entries. | Working as expected. | PASS | 1.0.0.4
TC-76 | Verify duplicate phone numbers | User is on Add Contact screen | Add the same phone number twice. | An error message is displayed, and duplicates are not allowed. | No Error msg displayed, the number is saved successfully twice but shown as only one entry | TBD | 1.0.0.4
TC-77 | Verify invalid email address | User is on Add Contact screen | Enter an invalid email address (e.g., "user@com" or "user.com"). | An error message is displayed, and the input is not accepted. | No, error msg or validation is shown and email is saved successfully | TBD | 1.0.0.4
TC-78 | Verify behavior when required fields are missing | User is on Add Contact screen | Leave one or more required fields blank and tap "Create New Contact." | An error message is displayed, and the contact is not created. | Validation only appears at First Name field | TBD | 1.0.0.4 | Contact is created successfully when user only enter the First Name and Leave Last Name, Contact # and Email field empty
TC-79 | Verify maximum character limit for Name fields | User is on Add Contact screen | Enter a very long name (e.g., 100+ characters) in the First Name or Last Name field. | Input is truncated or an error message is displayed if it exceeds the limit. | The contact is saved successfully | FAIL | 1.0.0.4
VIEW CREW SCREEN
TC-80 | Verify Crew Details Display | User is logged in and has created a crew. | 1. Navigate to the crew list. 2. Select a crew to view details. 3. Observe the displayed details on the screen. | Crew name, color theme, frequency, and member details are displayed correctly. | Working as expected. | PASS | 1.0.0.4
TC-81 | Verify Add New Contact Button Functionality | User is logged in and on the View Crew screen. | 1. Tap on the "Add new" button in the Members section. 2. Add a contact. 3. Save changes. 4. Navigate back to the View Crew screen. | New contact is added and displayed in the Members section. | New contact is added successfully in few crews and in few crews error of Invalid type Provided is appearing esp in crew REACTREE | FAIL | 1.0.0.4
TC-82 | Verify Delete Contact Functionality | User is logged in, on the View Crew screen, and a contact exists in the Members section. | 1. Tap the delete icon next to a contact. 2. Confirm the delete action. | Contact is removed from the Members section. | Some contacts are NOT deleting | FAIL | 1.0.0.4
TC-83 | Verify Reminder Icon for Each Member | User is logged in and on the View Crew screen with at least one member added to the crew. | 1. Check for the reminder icon next to each member in the Members section. 2. Tap the icon to set a reminder for the contact. | Reminder icon is visible for each member. Reminder settings open when tapped. | Working as expected. | PASS | 1.0.0.4
TC-84 | Verify Color Theme Display | User is logged in and viewing crew details. | 1. Observe the color theme displayed in the Settings section. 2. Verify that it matches the selected theme during crew creation or editing. | Correct color theme (e.g., Deep Saffron) is displayed. | Working as expected. | PASS | 1.0.0.4
CALENDER SCREEN
TC-85 | Verify contacts are grouped by date | User is logged in and on the Calender screen. | 1. Open the Calendar screen. 2. Check if contacts are displayed under their respective dates. | Contacts are correctly grouped under their corresponding dates. | Working as expected. | PASS | 1.0.0.4
TC-86 | Verify contact details display | User is logged in and on the Calender screen. | 1. Tap on any contact card. 2. Verify the displayed details (name, group, etc.). | Correct details (name, group) are displayed for the selected contact. | Working as expected. | PASS | 1.0.0.4
TC-87 | Verify navigation to contact details screen | User is logged in and on the Calender screen. | 1. Tap the ">" icon next to any contact. 2. Observe the navigation. | The app navigates to the contact details screen. | Working as expected. | PASS | 1.0.0.4
TC-88 | Verify group names and colors | User is logged in and on the Calender screen. | 1. Observe the group name and color below each contact. 2. Verify that different groups are displayed with their respective colors (e.g., Work: green). | Group names and colors are correctly displayed (e.g., New Crew: orange, Work: green). | Working as expected. | PASS | 1.0.0.4
TC-89 | Verify empty state for dates without contacts | User is logged in and on the Calender screen. | 1. Navigate to a date with no scheduled contacts. 2. Check the message or display. | An appropriate message (e.g., "No contacts scheduled") is displayed. |  |  | 1.0.0.4
TC-90 | Verify bottom navigation menu | User is logged in and on the Calender screen. | 1. Tap each icon (Home, Contacts, Calendar, Settings) in the bottom navigation bar. 2. Verify navigation to respective screens. | The bottom navigation menu is functional and navigates to the correct screens. | Working as expected. | PASS | 1.0.0.4
SETTINGS
TC-91 | Verify the presence of all options | User is logged in and on the Settings Screen. | 1. Open the Settings screen. 2. Verify the following options are displayed: - Account Information - Privacy and Settings - Notifications - Logout | All options are visible and correctly labeled. | Working as expected. | PASS | 1.0.0.4
TC-92 | Verify the display of account information | User is logged in and on the Account Information Screen | 1. Open the Account Information screen. 2. Check the fields: First Name, Last Name, and Email. | Fields are displayed correctly with accurate values. | Working as expected. | PASS | 1.0.0.4
TC-93 | Verify navigation back to the Settings screen | User is logged in and on the Account Information Screen | 1. Tap the back arrow on the top-left corner. 2. Observe the navigation. | Navigates back to the Settings screen. | Working as expected. | PASS | 1.0.0.4
TC-94 | Verify the Edit button functionality | User is logged in and on the Account Information Screen | 1. Tap the Edit button. 2. Observe the navigation. | Navigates to the Edit Account Information screen. | Working as expected. | PASS | 1.0.0.4
TC-95 | Verify user can edit first name and last name | User is on Edit Account Info screen | 1. Tap on the First Name and Last Name fields. 2. Enter new values. 3. Tap "Save changes." | Updated names should be reflected on both Edit and Account Info screens. | Working as expected. | PASS | 1.0.0.4
TC-96 | Verify email cannot be edited | User is on Edit Account Info screen | 1. Attempt to modify the email field. 2. Verify whether the field is editable. | Email field should not be editable. | Working as expected. | PASS | 1.0.0.4
TC-97 | Verify "Change Password" option functionality | User is on Edit Account Info screen | 1. Tap "Change Password?" link. 2. Verify redirection to the password reset process. | User is redirected to the password reset screen. | Working as expected. | PASS | 1.0.0.4
TC-98 | Verify Password Masking Button Behavior | User is on Edit Account Info screen | 1- Navigate to the Account Information screen. 2- Locate the password field and tap the eye icon (password masking/unmasking button). | The button should toggle between showing and hiding the password. | Tapping the button redirects the user to the Change Password screen. | FAIL | 1.0.0.4
TC-99 | Verify Sticky Email Copy Button | User is on Edit Account Info screen | 1- Navigate to the Account Information screen. 2- Select the email field to bring up the "Copy" or "Select All" options. 3- Tap "Copy" or "Select All." 4- Navigate to other screens in the app. | The "Copy" or "Select All" button should disappear once the action is complete. | The button remains visible and sticks to all screens in the app. | FAIL | 1.0.0.4
TC-100 | Verify "Delete account" button functionality | User is on Edit Account Info screen | 1. Tap "Delete account." 2. Confirm deletion. | Account should be deleted, and the user redirected to the app’s login/signup screen. | Account deletion request will be sent to the administrator | TBD | 1.0.0.4
TC-101 | Verify "Save changes" button functionality | User is on Edit Account Info screen | 1. Make valid changes to editable fields. 2. Tap "Save changes." | Changes should be saved, and user redirected to the Account Information screen. | Working as expected. | PASS | 1.0.0.4
TC-102 | Verify the user’s ability to edit account information | User is logged in and on the Account Information Screen | 1. Tap the Edit button. 2. Modify any field (e.g., First Name or Last Name). 3. Save changes. | Changes are saved and reflected correctly on the Account Information screen. | Working as expected. | PASS | 1.0.0.4
TC-103 | Verify the email field is not editable | User is logged in and on the Account Information Screen | 1. Tap the Edit button. 2. Try to modify the Email field. 3. Save changes. | The Email field remains non-editable and unchanged. | When keep pressing email it shows copy or select all option and that option remain throughout the screen | PASS | 1.0.0.4 | The masking button of change password is NOT working instead it redirects to the change Password screen
TC-104 | Verify data consistency after editing | User is logged in and on the Account Information Screen | 1. Edit any field (e.g., First Name). 2. Navigate back to the Settings screen. 3. Reopen Account Information. | Updated data persists and displays correctly. | Working as expected. | PASS | 1.0.0.4
TC-105 | Verify navigation to Privacy and Settings | User is logged in and on the Settings Screen. | 1. Tap on Privacy and Settings. 2. Observe the navigation. | Navigates to the Privacy and Settings screen. | NOT WORKING ATM | WIP | 1.0.0.4
TC-106 | Verify navigation to Notifications | User is logged in and on the Settings Screen. | 1. Tap on Notifications. 2. Observe the navigation. | Navigates to the Notifications screen. | Working as expected. | PASS | 1.0.0.4
TC-107 | Verify that the notification time is editable | App is running, and the Notification screen is open. | 1. Tap on the "Notification time" field. 2. Select a different time. | The selected time is displayed in the "Notification time" field. | Working as expected. | PASS | 1.0.0.4
TC-108 | Verify that notifications can be enabled | App is running, and the Notification screen is open. | 1. Toggle the "Allow notifications" switch to ON. | The switch changes to ON, enabling notifications. | Working as expected. | PASS | 1.0.0.4
TC-109 | Verify that notifications can be disabled | App is running, and the Notification screen is open. | 1. Toggle the "Allow notifications" switch to OFF. | The switch changes to OFF, disabling notifications. | Working as expected. | PASS | 1.0.0.4
TC-110 | Verify that the Save button saves the notification settings | App is running, and the Notification screen is open. | 1. Make changes to "Notification time" or toggle the notification permission. 2. Tap the "Save" button. | The updated notification time and permissions are saved successfully. | Working as expected. | PASS | 1.0.0.4
TC-111 | Verify input validation for Notification time | App is running, and the Notification screen is open. | 1. Enter invalid or blank time input (if applicable). 2. Try to save. | App displays a validation error and prevents saving invalid input. | Working as expected. | PASS | 1.0.0.4
TC-112 | Verify navigation back to the previous screen | App is running, and the Notification screen is open. | 1. Tap on the back button (top-left arrow icon). | User is navigated back to the previous screen. | Working as expected. | PASS | 1.0.0.4
TC-113 | Verify the Logout functionality | User is logged in and on the Settings Screen. | 1. Tap on Logout. 2. Confirm the action if prompted. 3. Observe the result. | User is logged out and redirected to the login screen. | Working as expected. | PASS | 1.0.0.4

## ISSUES
INNER CREW
SNO. | OBSERVATIONS | STEPS TO REPRODUCE | TYPE | DEV STATUS | TESTING STATUS | ACTUAL RESULT (1.0.0.4) | ACTUAL RESULT (1.0.0.6) | Notes
1 | Tag update issue on the Home Screen after frequent edits. |  |  |  |  | This is working ok now
2 | No notification received when the toggle time is set to 1 PM and the app is closed. | Set the notification timing from the notification settings and observe the app notification when app is closed |  | In-Progress |  | NOT WORKING
3 | "INVALID TYPE PROVIDED" error occurs when adding a user to a crew. | When adding contacts in a crew. This behaviour is appearing randomly | Bug | Done | Done | working | tested on build 1.0.0.6 and this issue still present
4 | Crew display picture (DP) color appears and disappears intermittently. | 1- Set the display picture (DP) for a crew. 2- Close the app. 3- Reopen the app. 4- Navigate to the Contacts screen. 5- Observe that the DP does not appear for the crew. Instead, the crew displays the theme color. 6- Tap on the affected crew. 7- Notice that the DP color turns white. | Bug | Done | Done | working | Inconsistent behavior. sometimes appearing grey and some times dp shows. |  | sync contact
5 | Crew display picture (DP) keeps loading continuously when viewing the crew. | 1- Open the app. 2- Navigate to the Contacts screen. 3- Tap on VIEW CREW. 4- Observe that the profile picture keeps loading. 5- Note that the profile picture is displayed only after 30-40 seconds. | Bug | Done | Done | working | working |  | add contact
6 | Crew member's display picture (DP) is removed unexpectedly. |  |  | Done | Done | This is working ok now | ok |  | edit contact
7 | When editing a contact and selecting a crew at the bottom, the crew DP does not update. | 1- Set the display picture (DP) for the Family crew. 2- Navigate to the Work crew, which already has contacts. 3- Select any contact from the Work crew. 4- Go to Edit Details for the selected contact. 5- At the bottom, select the Family crew (the crew whose DP was previously set). 6- Observe that a white screen appears in place of the DP for the Family crew. | Bug | Done | Done | working | ok
8 | Crew description cannot be deleted. Once it is set, even after removing and updating it, the same information reappears. |  |  | Done | Done | This is working ok now | tested on build 1.0.0.6 and this issue still present
9 | When make changes in any contact and save it, it first shows toast of Contact Updated then shows toast of Contact Not Found | 1- Open the app and navigate to the Crew section. 2- Edit the details of any contact within the crew. 3- Tap on the Update Crew button. 4- Observe that toasts appear upon updating. | Bug | Done | Done | working | ok
10 | Last Name is NOT properly removed when editing a crew contact. | 1- Open the app and navigate to the Crew section. 2- Select a contact with the name: - First Name: Muhammad - Last Name: Hasan 1 3- Edit the contact's details: - Change First Name to "HASAN". - Leave the Last Name field empty. 4- Save the changes. 5- Go to the Home screen and refresh it. 6- Observe that the contact's name displays as "HASAN Hasan 1" instead of "HASAN". | Bug | Done | Done | working | ok
11 | Delete a contact from crew is not working properly for few contacts | Delete a contact; it disappears temporarily from the crew's screen but still appears on the Contacts screen and in the crew details upon revisiting. | Bug | Done | Done | working | tested on build 1.0.0.6 and this issue still present
12 | When Login again with already registered Account with contacts added, it first shows the screen "Seems like you haven't added any contacts yet" then redirect to the Home Screen | 1- Open the app 2- Enter already registered credentials 3- Observe it first shows the screen "Seems like you haven't added any contacts yet" then redirect to the Home Screen | Bug | In-Progress |  |  | tested on build 1.0.0.6 and this issue still present
13 | The group tag color (e.g., orange for "Family") displayed in the Contact Summary section is static and does not change dynamically based on the actual group settings. | 1- Navigate to the Home screen. 2- Tap on a contact card (e.g., "Call A"). 3- Observe the Contact Summary section, particularly the group tag color. | Bug | Done | Done | working | ok
14 | Log Sync Popup Not Displaying on Android and iOS |  | Bug | In-Progress
15 | Shimmer effect appears when open any contact | 1- Navigate to the Home Screen 2- Open any Contact 3- Tap on View 4- Observe the Shimmer appears at No past calls found | Bug | Done | Done | working | ok
16 | Black color floating button of Add your first contact is appearing on Add Contact screen | 1- Navigate to the Home screen 2- Tap the "Add people" button. | Bug | Done | Done | working | ok
17 | Selecting the email field and tapping "Copy" or "Select All" causes the button to stick across the entire app. | 1- Navigate to the Account Information screen. 2- Select the email field to bring up the "Copy" or "Select All" options. 3- Tap "Copy" or "Select All." 4- Navigate to other screens in the app. | Bug | Done | Done | working | tested on build 1.0.0.6 and this issue still present
18 | On Account Information screen, tapping on the password masking button incorrectly redirects the user to the "Change Password" screen. | 1- Navigate to the Account Information screen. 2- Locate the password field and tap the eye icon (password masking/unmasking button). | Bug | Done | Done | working | Eye icon is not working now
19 | Contact Duplication Across Accounts and Grey Screen Display | 1. Log in to Account A. 2. Save a new contact in Account A. 3. Log out of Account A. 4. Log in to Account B. 5. Check the contact list in Account B. 6. Tap on the duplicated contact in Account B. | Bug | Done | Done | working | ok
20 | Contacts Saved with Incorrect Formatting and Grey Screen on Tap | 1. Add a contact similar to the highlighted one in screenshot provided. 2. Navigate to the "Calendar" section. 3. Locate the added contact. 4. Tap on the highlighted contact. | Bug | Done | Done | working | tested on build 1.0.0.6 and this issue still present
test34@gmail.com Added A.G. Bhatt contact → Grey screen appeared. Deleted the previous contact. Added a new contact. After adding the new contact, the previously deleted contacts also reappeared.
test35@gmail.com added normal mobile contacts > Grey screen appears after sometimes the normal contact screen will appear
Get it tested on Android 14 > Working OK
Get it tested on Android 11 > Working OK

## SCREENSHOTS
2- | No notification received when the toggle time is set to 1 PM and the app is closed.
3- | "INVALID TYPE PROVIDED" error occurs when adding a user to a crew.
4- | Crew display picture (DP) color appears and disappears intermittently.
5- | Crew display picture (DP) keeps loading continuously when viewing the crew.
7- | When editing a contact and selecting a crew at the bottom, the crew DP does not update.
9- | When make changes in any contact and save it, it first shows toast of Contact Updated then shows toast of Contact Not Found
11- | Last Name is NOT properly removed when editing a crew contact.
12- | When Login again with already registered Account with contacts added, it first shows the screen "Seems like you haven't added any contacts yet" then redirect to the Home Screen
13- | Static color for the group tag in the contact summary on the Home screen.
16- | Black color floating button of Add your first contact is appearing on Add Contact screen
17 & 18 | Sticky Email Copy Button & Password Masking Button Behavior
19 | Contact Duplication Across Accounts and Grey Screen Display
20 | Contacts Saved with Incorrect Formatting and Grey Screen on Tap

## Sheet7
Production Build: 1.0.0.11
TESTING OBJECT:
i- | Notifications coming on foreground, background, terminated states. coordinate with ahmed on this.
ii- | Sync popup coming on app startup and later when you make calls and resume the app
SNO. | Test Scenario | Precondition | Steps to Execute | Expected Result | Actual Result
1 | Notification in Foreground State | App is open and in use | 1. Keep the app open. 2. Send a notification to the user. | Notification will appear | Notification is received
2 | Notification in Background State | App is running in the background | 1. Minimize the app (press the home button). 2. Send a notification. | Notification will appear | Notification is received
3 | Notification in Terminated State | App is completely closed | 1. Force close (kill) the app. 2. Send a notification. | Notification will appear | Notification is received
4 | Notification when Logged In | User is logged into the app | 1. Stay logged in. 2. Send a notification. | Notification will appear | Notification is received
5 | Notification when Logged Out | User has logged out | 1. Log out of the app. 2. Send a notification. | Notification should NOT be received as the user is logged out. | Notification is NOT received
6 | Notification After Logging Out and Logging In Again | User logs out and logs in again | 1. Log out of the app. 2. Log in again. 3. Send a notification. | Notification should be received as per the user’s app state (foreground, background, or terminated). | Notification is received
7 | Notification After Switching Accounts | User logs into a different account | 1. Log out of the app. 2. Log in with another account. 3. Send a notification to the previous account. | The previous account should NOT receive the notification. The new account should receive only its relevant notifications. | Notification from the previous account is received on the current account.
8 | Notification While Device is Locked | App is running in any state | 1. Lock the device screen. 2. Send a notification. | Notification will appear | Notification is received
9 | Notification with Different Permissions (Enabled/Disabled) | App notification permissions are turned ON/OFF | 1. Disable app notifications in device settings. 2. Send a notification. | If disabled, notification should not appear. If enabled, it should work as expected. | Notification not received on disabled Notification received on enabled
10 | Sync popup coming on app startup | App is installed, user is logged in | open the app | Sync popup should appear if sync is required | Sync pop-up is appearing
11 | Sync popup coming later when you make calls and resume the app | User makes a call from the app | Make a call and return to the app | Sync popup should appear if new data needs to be synced | Sync pop-up is appearing