## Sheet1 (hidden)
Tasks | ETA by Sofcom | Notes | Requested ETA | Sofcom Status | Reactree Status | Sofcom comments | Reactree comments
APIs Not Working
Allow Reportee To Change Objectives | 9th September | Align call with x - teams | 9th September | Done | Done
Self review submit api not working -> Interim Review | 9th September | Align call with x - teams | 9th September | Done | In Review |  | Will Review on 13th September
Draft and submit api of reportees review -> Interim Review | 9th September | Align call with x - teams | 9th September | Done | Draft: Done Submit: In Review |  | Will Review on 13th September
in appraisal only my appraisal rating api's are working | 12th September | Align call with x - teams | 11th September | Done | In Review
self appraisal apis | 12th September | Align call with x - teams | 11th September | Done | In Review
reportee appraisal apis | 12th September | Align call with x - teams | 11th September | Done | In Review
Appraisal Completed by Reportee(s) apis | 12th September | Align call with x - teams | 11th September | Done | In Review
Reportee Response api | 12th September | Align call with x - teams | 11th September | Done | In Review
APIs Not Available
Appraisal Review Pending Request | 11th Septmber | Yousha | 10th Septmber | Done | Api Not Available | pending request and approval will be provided tomorrow. | 2nd Half
Final Appraisal Pending Requets
Promotion Recommendation Pending Request
Employee Objective Pending Request
Change Objective Pending Request
Self Appraisal Pending Request
Self Review Pending Request
Appraisal Review Pending Approval
Final Appraisal Pending Approval
Promotion Recommendation Pending Approval
Employee Objective Pending Approval
Change Objective Pending Approval
Self Appraisal Pending Approval
Self Review Pending Approval | 11th Septmber | Yousha | 10th Septmber | In Progress | Done |  | 2nd Half
Pending Request Resignation | 11th Septmber | Fatima | 10th Septmber | Done | Api not Available |  | Data Not Available
Pending Approval Resignation | 11th Septmber | Fatima | 10th Septmber | Done | Done |  | Data Not Available
Notification Screen Api | TBD | TBD
360 Appraisal (Available on Postman but comments not there on Figma) | 10th September | Fatima/Yousha | 9th September - 1st half | Done | In Review | Get API(s) missings. (360 appraisal api is available and updated on postman). view approver request body is also available on postman. Promotion get api is also available. the validate. approved appraisal apis is provided on postman | Done
Approved appraisal | 11th September | Yousha | 10th September -1st half | Done | In Review |  | Done
Promotion Recommendation (Available on Postman but comments not there on Figma) | 10th September | Fatima | 9th September - 1st half | Done | In Review |  | Done
appraisal reportee lookup id is missing. | 10th September | Yousha | 10th September | Done |  | postman collection was not updated. | Will Review on 13th September
what is the purpose of copy self appraisal and view self appraisal buttons on reportees review screen | 11th September | Yousha | 11th September | Done | In Review |  | API is updated on postman collection
Print buttons in all over interim review | 11th September | Yousha | 11th September | Done | In Review |  | Will Review on 13th September
revert appraisee functionality missing | 12th September |  | 11th September | In Progress
Screens Are On Preview But Not Reviewed
In Pending Request :
i ) Promotion Recommendation | 10th September | Yousha | EOD | Done | Done | appraisal pending request screen will be reviewed on 10th september | Will discuss with their head and update us till 2nd half
ii ) Appraisal Review | 10th September | Yousha | EOD | Done | In Review | appraisal pending request screen will be reviewed on 10th september | Yousuf will brief on changes
iii ) Resignation | 9th September | Yousha | EOD | Done | Done
iv) Final Appraisal | 10th September | Yousha | EOD | Done | In Review | appraisal pending request screen will be reviewed on 10th september | Will discuss with their head and update us till 2nd half
Screens Reviewed But Still Not Confirmed from their side
Pending Approval Screens:
i ) Promotion Recommendation | 10th September | Yousha | EOD | Done | Done | appraisal pending request screen will be reviewed on 10th september | Will discuss with their head and update us till 2nd half
ii ) Appraisal Review | 10th September | Yousha | EOD | Done | In Review | appraisal pending request screen will be reviewed on 10th september | Yousuf will brief on changes
iii ) Resignation | 9th September | Yousha | EOD | Done | Done
iv ) Final Appraisal | 10th September | Yousha | EOD | Done | In Review | appraisal pending request screen will be reviewed on 10th september | Will discuss with their head and update us till 2nd half
Miscellaneous
Leave Application | 10th September | Fatima |  | Done | In Review |  | Done

## New Issues (hidden)
No. | Tasks | Task Creation Date | ETA by Sofcom | Sofcom Status | Requested ETA | Reactree Status | Sofcom comments | Reactree comments
1 | Resignation Pending Request and Approval COMMENTS NOT AVAILABLE | 16th Sept | 19th Sept 2nd Half | Completed | 19th Sept | In-Review
2 | Appraisal Pending Request and Approval COMMENTS NOT AVAILABLE | 16th Sept | 19th Sept 2nd Half | Completed | 19th Sept | In-Review
3 | Appraisal Pending Request main screen DATA NOT AVAILABLE | 16th Sept | 19th Sept 2nd Half | Pending | 19th Sept
4 | Appraisal Pending Approval main screen DATA NOT AVAILABLE | 16th Sept | 19th Sept 2nd Half | Pending | 19th Sept
5 | Employee Objective Pending Request DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Completed | EOD | In-Review | on emp id 22 with requestId EO20240700000024 | ok | You can find tons of data on Emp Id 2 and EmpId 9
6 | Employee Objective Pending Approval DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Completed | EOD | In-Review | on emp id 2 with request id EO20240700000024 | ok
7 | Change in Employee Objective Pending Request DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Completed | EOD | In-Review | on emp id 22 with request id CO20240900000002 | ok
8 | Change in Employee Objective Pending Approval DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Completed | EOD | In-Review | on emp id 2 with request id CO20240900000002 | ok
9 | Self Appraisal Pending Request DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Completed | EOD | In-Review | on emp id 22 with requestId SA20210100000001 | ok
10 | Self Appraisal Pending Approval DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Completed | EOD | In-Review | on emp id 1 with requestId SA20210100000001 | not available
11 | Self Review Pending Request DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Completed | EOD | In-Review | on emp id 22 with requestId SR20240700000004 | ok
12 | Self Review Pending Approval DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Completed | EOD | In-Review | on emp id 1 with requestId SR20240700000004 | ok
13 | Revert Appraisee functionality missing | 16th Sept | 16th Sept 2nd Half | Completed | EOD | In-Review | the api is provided and updated on postman. kindly check its documentation for integeration. comments on figam is also added
14 | E-Learning DATA NOT AVAILABLE | 16th Sept |  | Pending | 20th Sept
15 | Eligible Employees ID | 16th Sept | 16th Sept 1st Half | Completed | 16th Sep 1st Half | Accepted | find eligible employees on emp id 9 | Working Ok
16 | Promotion Recommendation ID | 16th Sept | 16th Sept 1st Half | Completed | 16th Sep 1st Half | Accepted | find promotion recommendation on emp id 87 with policyCode =2016 | Working OK
17 | 360 degree Appraisal Form Screen functionality API NOT WORKING | 16th Sept |  | Completed | 18th Sept | Accepted | We are targeting development to be end at the end of September. therefore not data will be provided and the team will be focusing on development only.
18 | Past Appraisal Proceed functionality DATA NOT AVAILABLE IN APIS | 16th Sept | 22th Sept 2nd Half | Pending | 19th Sept
19 | Pending Request Loan screen detail fuctionality DATA NOT AVAILABLE IN APIS | 16th Sept | 22th Sept 2nd Half | Pending | 19th Sept
20 | Pending Approval Loan screen detail fuctionality DATA NOT AVAILABLE IN APIS | 16th Sept | 22th Sept 2nd Half | Pending | 19th Sept
21 | Direct Reportees Review UI/UX DATA NOT AVAILABLE | 16th Sept | 22th Sept 2nd Half | Pending | 19th Sept
22 | Direct Reportees Final Appraisal UI/UX DATA NOT AVAILABLE | 16th Sept | 22th Sept 2nd Half | Pending | 19th Sept
23 | Direct Reportees Bell Curve UI/UX DATA NOT AVAILABLE | 16th Sept | 22th Sept 2nd Half | Pending | 19th Sept
24 | Direct Reportees Bell Curve functionality DATA NOT AVAILABLE | 16th Sept | 22th Sept 2nd Half | Pending | 19th Sept
25 | Direct Reportees Final Performance UI/UX DATA NOT AVAILABLE | 16th Sept | 22th Sept 2nd Half | Pending | 19th Sept
26 | Direct Reportees Final Performance functionality DATA NOT AVAILABLE | 16th Sept | 22th Sept 2nd Half | Pending | 19th Sept
27 | Request History Screens Are On Preview But Not Reviewed | 18th Sept | 22th Sept 2nd Half | Pending | 19th Sept
28 | Important Documents Screens Are On Preview But Not Reviewed | 18th Sept | 22th Sept 2nd Half | Pending | 19th Sept
29 | Api refactoring of Pending Request Details (Resignation), Add List of active loans to it | 18th Sept | 22th Sept 2nd Half | Pending | 19th Sept
31
32
33
34
35
36

## Final Sheet
No. | Tasks | Task Creation Date | ETA by Sofcom | Sofcom Status | Provided On | Requested ETA | Reactree Status | Sofcom comments | Reactree comments
1 | Request History API no available | 30th Sept | 2nd Oct | API Provided |  | 2nd Oct | Completed |  | ok
2 | FCM with Request History | 30th Sept | 2nd Oct | Data Provided |  | 2nd Oct | Completed | routes, response. FCM Properties such as marked as read. | ok
3 | Loan(A lot of work is done based on dummy data and is failing with real data) Proper data not available | 30th Sept | 2nd Oct | Data Provided |  | 2nd Oct | Not Working |  | Loan data is NOT working
4 | E-Learning - Data not available | 30th Sept | 2nd-4th Oct (18th Oct, New ETA) | Data Provided |  | 2nd Oct | In-Progress |  | E-learning data available with Emp.ID 7, Except Assesment in Scorm data
5 | Past Appraisal Working With Real Data - Real Data not there | 30th Sept | 2nd Oct | Data Provided |  | 2nd Oct | Working |  | as per discussion, in Past Appraisal, is the dummy data the same as the Self Appraisal data
6 | Important Documents | 30th Sept | 2nd Oct | Data Provided |  | 2nd Oct | Working |  | ok
9 | Employee Objective Pending Request DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | Working | on emp id 22 with requestId EO20240700000024 | ok
10 | Employee Objective Pending Approval DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | Working | on emp id 2 with request id EO20240700000024 | ok
11 | Change in Employee Objective Pending Request DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | Working | on emp id 22 with request id CO20240900000002 | ok
12 | Change in Employee Objective Pending Approval DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | Working | on emp id 2 with request id CO20240900000002 | ok
13 | Reportee Appraisal Pending Request DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  |  | Not Working | Emp ID: 41 Select Appraisal Policy 2024 | NOT Working
14 | Reportee Appraisal Pending Approval DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  |  | Not Working | Emp ID: 9 Select Appraisal Policy 2024 | NOT Working
15 | Self Appraisal Pending Request DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | Working | on emp id 22 with requestId SA20210100000001 | ok
16 | Self Appraisal Pending Approval DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | Not Working | on emp id 55 with requestId SA20241000000002 | not available
17 | Self Review Pending Request DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | Working | on emp id 22 with requestId SR20240700000004 | ok
18 | Self Review Pending Approval DATA NOT AVAILABLE | 16th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | Working | on emp id 1 with requestId SR20240700000004 | ok
19 | Promotion Recommendation Pending Request DATA NOT AVAILABLE | 11th Sept | 16th Sept 2nd Half | Pending |  | EOD |  |  | Data Still not provided by SOFCOM
20 | Promotion Recommendation Pending Approval DATA NOT AVAILABLE | 11th Sept | 16th Sept 2nd Half | Pending |  | EOD |  |  | Data Still not provided by SOFCOM
21 | Appraisal Review Pending Request DATA NOT AVAILABLE | 11th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | In-Review | Emp.ID 7 & 55 App. Policy 2024 | Data Provided by SOFCOM on 11th Oct
22 | Appraisal Review Pending Approval DATA NOT AVAILABLE | 11th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | In-Review | Emp.ID 7 & 55 App. Policy 2024 | Data Provided by SOFCOM on 11th Oct
23 | Final Appraisal Pending Request DATA NOT AVAILABLE | 11th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | In-Review | Emp ID 41 LM 9 Emp 7 or 9 LM 2 | Data Provided by SOFCOM on 11th Oct
24 | Final Appraisal Pending Approval DATA NOT AVAILABLE | 11th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | In-Review | Emp ID 41 LM 9 Emp 7 or 9 LM 2 | Data Provided by SOFCOM on 11th Oct
| Review Appraisal Pending Request DATA NOT AVAILABLE | 11th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | In-Review | Emp.ID 7 & 55 & 2 App. Policy 2024 | Data Provided by SOFCOM on 11th Oct
| Review Appraisal Pending Approval DATA NOT AVAILABLE | 11th Sept | 16th Sept 2nd Half | Data Provided |  | EOD | In-Review | Emp.ID 7 & 55 & 2 App. Policy 2024 | Data Provided by SOFCOM on 11th Oct
25 | Revert Appraisee functionality missing | 16th Sept | 16th Sept 2nd Half | API Provided |  | EOD | Working | the api is provided and updated on postman. kindly check its documentation for integeration. comments on figam is also added | API is working. Dev work is remaining.
26 | Loan Pending Request testing with real data | 30th Sept | 4th Oct | Data Provided |  | EOD | Working | Emp ID: 9 | ok
27 | Loan Pending Approval testing with real data | 30th Sept | 4th Oct | Data Provided |  | EOD | Working | Emp ID: 2 | ok
28 | Notification Screen UI | 30th Sept |  | In-Review |  | 7th Oct | Completed |  | Notification screen UI available on FIGMA
29 | Notification Screen APIs status | 30th Sept |  | In-Progress |  | EOD |  |  | Not provided by SOFCOM
30 | RDLCs for Summary in Expense and RDLC in Attendance Comments and APIs required | 30th Sept | 2nd Oct First Half | API Provided |  | EOD | Completed |  | Figma comments and API required
31 | Appraisal Analysis Beautification | 30th Sept |  | In-Review |  | EOD | Completed |  | Appraisal Analysis beautification work is done from our end.
32 | Refactored apis for Special, Planned etc Comments NOT available | 30th Sept | 2nd Oct First Half | Completed |  | EOD | Completed |  | Figma Comments Required
33 | missing back navigation in MSS Team Reportee Profile | 2nd Oct | 2nd Oct First Half | In-Review |  | EOD | Completed |  | Completed from our end
8 | Reportees on Leave today DATA REQUIRED FOR TRANSLATION | 6th Nov | 6th Nov First Half | Data Provided | 12th Nov | 6th Nov First Half | Working | LM ID 2

## Customization
CUSTOMIZATION TASKS
No. | Tasks | Task Creation Date | Priority | ETA by Sofcom | Sofcom Status | Provided On | Requested ETA | Reactree Status | Sofcom comments | Reactree comments
1 | Mark Attendance on Official Duty DATA NOT AVAILABLE | 4th Nov | High | 4th Nov 2nd Half | Data Provided | 5th Nov | 5th Nov 2nd Half | Working | Emp ID: 7
2 | Mark Attendance on Official Visit DATA NOT AVAILABLE | 4th Nov | High | 4th Nov 2nd Half | Data Provided | 5th Nov | 5th Nov 2nd Half | Working | Emp ID: 7
3 | Project Management (Rejected Time Sheet) DATA NOT AVAILABLE | 7th Oct | Medium | 6th Nov First Half | Data Provided | 15th Nov | 10th Oct | Working | Emp.ID: 23
4 | Career Management DATA NOT AVAILABLE | 7th Oct | Medium | 6th Nov First Half | Data Provided | 12th Nov | 6th Nov First Half | Working | Emp ID: 1
5 | Interview Evaluation DATA NOT AVAILABLE | 7th Oct | Low | 6th Nov First Half | Data Provided | 19th Nov | 6th Nov First Half | Working | Below options data available in Interviews with Emp 7 - Schedule Interview - Rejected Interview - Conducted Interview - Locked Interview | Accepted Interview Data has NOT provided yet
6 | Hourly Leaves (customization) DATA NOT AVAILABLE | 6th Nov | Medium | 6th Nov First Half | Data Provided | 8th Nov | 6th Nov First Half | Working | Emp 61 / 55 and LM ID 33 | Data Available and Working
7 | Modify Leaves (customization DATA NOT AVAILABLE | 6th Nov | Medium | 6th Nov First Half | Data Provided | 8th Nov | 6th Nov First Half | Working | Emp 61 and LM ID 7
8 | Payroll Edit Bank Information DATA NOT AVAILABLE | 11th Nov | Ciritical | 12th Nov First Half | Data Provided | 13th Nov | 13th Nov First Half | Working | Emp ID: 22 and LM: 1 in Pending Approval > Miscellaneous
9 | HR Helpdesk (General Request Form) DATA NOT AVAILABLE | 11th Nov | Medium | 12th Nov First Half | Data Provided | 14th Nov | 13th Nov First Half | Working | General Request Form, Adhoc Approval > Emp 7 and LM 1 for Help Desk General Request select Transport Request
10 | Resignation Exit Type Lookup DATA NOT AVAILABLE | 11th Nov | Medium | 12th Nov First Half | Data Provided | 20th Nov | 13th Nov First Half | Working | Emp ID 9 and 7
11 | Medical (Customization Tasks + DATA required) | 11th Nov | Low | 12th Nov First Half | Pending |  | 13th Nov First Half
12 | Confirmation (Customization Tasks + DATA required) | 11th Nov | Medium | 12th Nov First Half | Pending |  | 13th Nov First Half
13 | Appraisal data NOT working | 7th Nov | High | 8th Nov First Half | Pending |  | 6th Nov First Half |  | Appraisal Policy 2024 Objectives 1:- My objectives 2:- View Reportee Objectives Appraisal 1:- Self Appraisal Check Emp 22